## Sheet1
Facility Name | Project Title | Current Phase | Occupancy Complete | Project Manager
Andrews Hall | GRU Replacement (B44) | Design | 2025-01-09 | Thomas Foskett
Baurs & Holley | Phase 3 Renewal | Construction | 2025-08-29 | Jarred Jackson
Campus | Decarbonization Roadmap | Design | 2039-12-31 | Robert McCabe
Campus | Emergency 11kv Primary Feeder Replacement | Construction | 2025-01-01 | Robert McCabe
Campus | HVAC Controls | Construction | 2025-06-30 | Thomas Foskett
Campus | JD Decarbonization Strategy | Design | 2027-02-26 | Bill Lynch
Campus | Piping RepairsAllowance | Construction | 2025-06-30 | Robert McCabe
Campus | Standby Boiler Plant (Short Term Resiliency) | Construction | 2025-01-31 | Robert McCabe
Campus | Utility Systems Renewal and Upgrades (Ph 7 - Project 4 Elec MP) | Design | 2025-06-30 | Robert McCabe
Campus | Utility Systems Renewal and Upgrades (Ph 7 - Project 6) | Construction | 2025-07-01 | Robert McCabe
Central Heat Plant | Pizzitola HTHW Bypass | Construction | 2025-01-01 | Robert McCabe
Cushing Street 172 | Roof Replacement and Exterior Paint | Design | 2025-04-15 | Gary Martins
Davol Square 001 | Enabling: Admissions Center Project | Design | 2025-08-15 | Marcus Hurley
Davol Square 001 | Haffenreffer Collections Research Center | Construction | 2025-08-15 | Marcus Hurley
Geo-Chem Building | Geo-Chem PCHW & CA Renewal | Design | 2025-12-31 | Jarred Jackson
Hope College | MH-1031 Electrical Switch Relocation | Construction | 2024-12-31 | Robert McCabe
John Hay Library | Exterior Restoration and Repairs | Construction | 2025-06-30 | Thomas Foskett
Lyman Hall | Exterior Storefront Replacement & Access on South and North Elevations | Design | 2025-08-30 | Thomas Foskett
Manning Hall | Admissions Center | Design | 2025-10-24 | Marcus Hurley
Meiklejohn House | Boiler Replacement | Design | 2025-09-30 | Raymond Bourcier
Meister-Kavan Field | Indoor Turf Facility | Construction | 2026-01-16 | Paul Griffin
Multiple | ADA Gap Projects | Construction | 2025-04-18 | Yi Vizard
Multiple | Sidewalks Allowance | Construction | 2025-06-30 | Gary Martins
Multiple | ADA Lift Replacement | Construction | 2025-06-30 | Thomas Foskett
Multiple | Blue Lights at Sayles Hall and corner of George & Brown | Construction | 2025-06-30 | Gary Martins
Multiple | Chiller Allowance | Design | 2025-04-30 | Raymond Bourcier
Multiple | Classroom Allowance | Construction | 2025-06-30 | Gary Martins
Multiple | Controller Allowance | Construction | 2025-06-27 | Thomas Foskett
Multiple | Decarbonization - Heat Exchanger Replacements | Construction | 2027-06-01 | Robert McCabe
Multiple | Exterior Paint Allowance | Construction | 2025-06-30 | Gary Martins
Multiple | HTHW Unplanned Repairs | Construction | 2025-05-01 | Robert McCabe
Multiple | Leak Allowance/Water Intrusion Mitigation Program | Construction | 2025-09-01 | Yi Vizard
Multiple | Minor Roofing Allowance | Construction | 2025-06-30 | Gary Martins
Multiple | Parking Lot Allowance | Construction | 2025-06-30 | Gary Martins
Multiple | Partnership Allowance | Construction | 2025-06-30 | Gary Martins
Multiple | Pathways Allowance | Construction | 2025-06-30 | Gary Martins
OMAC | Football Locker Room & Office Upgrades and Lobby Improvements | Design | 2025-08-30 | Thomas Foskett
Page-Robinson Hall | Interior Renewal | Construction | 2025-01-19 | Thomas Foskett
Pizzitola | Video Board (101) | Construction | 2024-12-27 | Paul Griffin
Residence Halls | Hot Water Tank Installation | Construction | 2025-01-17 | Thomas Foskett
Richmond Street 233 | Danoff Laboratories | Construction | 2027-05-12 | Bill Lynch
Rockefeller Library | Interior Shell Renewal | Construction | 2025-04-30 | Yi Vizard
Ship Street 70 | Mass Spectrometry Feeder (413) | Design | 2025-01-31 | Jarred Jackson
Ship Street 71 | Enabling: Danoff Laboratories Bridge Lobby Renovation (310) | Design | 2025-09-26 | Bill Lynch
Sidney Frank Hall for Life Sciences | Standby Generator Docking Station | Design | 2025-02-28 | Robert McCabe
Simmons Quad | FS Piping Leak Repair | Construction | 2025-05-30 | Robert McCabe
Simmons Quad | Simmons Quad Landscape Design Study: Accessibility & Amphitheater | Design | 2025-10-17 | Marcus Hurley
South Main Street 121 | Fire Alarm/Protection/Egress Investigation | Design | 2025-01-10 | Raymond Bourcier
Utilities/Infrastructure | Utility Systems Renewal & Upgrades Ph 7 - Project 1 & 2) | Construction | 2025-07-01 | Robert McCabe
Watson CIT | OIT Data Center Power-Cooling | Construction | 2027-06-30 | Robert McCabe